## Website Project Data
Task | Assigned To | Start Date | End Date | Duration in Days
Market Research and Analysis | Carlos | 2023-07-05 | 2023-07-19 | 14
Define Product Assortment | Priya | 2023-07-20 | 2023-07-27 | 7
Pricing Strategy and Cost Analysis | Kai | 2023-07-22 | 2023-07-29 | 7
Website Development | Isabella | 2023-08-01 | 2023-08-15 | 14
User Experience Testing | Nia | 2023-08-18 | 2023-08-23 | 5
Marketing and Promotion Plan | Carlos | 2023-09-01 | 2023-09-30 | 30
Soft Launch and Testing | Isabella | 2023-10-01 | 2023-10-30 | 30